## Basic Gantt Chart
GANTT CHART Project 4 EECS 448
Eric, Earving, Travis, Lauren
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Initial Setup
| Make UML Diagrams | 2019-04-12 | 2019-04-15 | 0 | 3 | Eric | 100%
| SCRUM Initial | 2019-04-12 | 2019-04-15 | 0 | 3 | All | 100%
| Github Creation, tasks defined | 2019-04-12 | 2019-04-15 | 0 | 3 | Earving | 100%
| Gantt Chart | 2019-04-12 | 2019-04-15 | 0 | 3 | Eric | 100%
SET 1: MVP Tasks
| Basic web design stuff | 2019-04-12 | 2019-04-15 | 0 | 3 | Lauren | 100%
| Wild cards, 1 player vs. 1 - 3 bots 4 bots | 2019-04-12 | 2019-04-15 | 0 | 3 | Earving | 100%
| Show last 5 past cards played on playfield | 2019-04-12 | 2019-04-15 | 0 | 3 | Travis | 100%
SET 2: Eric's stuff/MVP finishing
| Uno call when a player has 1 card left | 2019-04-15 | 2019-04-17 | 3 | 2 | Eric | 100%
| * Must call uno before playing hand | 2019-04-15 | 2019-04-17 | 3 | 2 | Eric | 100%
| * Fail to call: +2 cards auto | 2019-04-15 | 2019-04-17 | 3 | 2 | Eric | 100%
| Test Suite - Automatic? Research | 2019-04-15 | 2019-04-17 | 3 | 2 | Lauren/Earving/Travis | 100%
SET 3: Enhancements phase 1
| View rules in new HTML page | 2019-04-17 | 2019-04-20 | 5 | 3 | Eric | 100%
| Lift card in hand on mouse-over/Mouse hover over cards spreads them out | 2019-04-17 | 2019-04-20 | 5 | 3 | Earving | 100%
| Add CSS styling to cards, change playfield card to match chosen wild card color | 2019-04-17 | 2019-04-20 | 5 | 3 | Lauren | 100%
| Forced to play valid card if one exists in hand | 2019-04-17 | 2019-04-20 | 5 | 3 | Travis | 100%
SET 4: Enhancements phase 2
| Start menu with options to choose from? | 2019-04-20 | 2019-04-24 | 8 | 4 | Lauren | 100%
| Make special cards more rare | 2019-04-20 | 2019-04-24 | 8 | 4 | Eric | 100%
| Animations: Drawn cards 'zoom' to player | 2019-04-20 | 2019-04-24 | 8 | 4 | Earving | 100%
| History of plays in console/on screen? | 2019-04-20 | 2019-04-24 | 8 | 4 | Travis | 100%
SET 5: Enhancements phase 3
| Cheat/Debug commands through console | 2019-04-24 | 2019-04-27 | 12 | 3 | Eric | 100%
| Limit bot hand amount to fit screen | 2019-04-24 | 2019-04-27 | 12 | 3 | Lauren | 100%
| Bug fixes | 2019-04-24 | 2019-04-27 | 12 | 3 | Earving | 100%
| Fancy uno calling logic | 2019-04-24 | 2019-04-27 | 12 | 3 | Travis | 75%
SET 6: Documentation & Plans
| HTML Documentation page | 2019-04-27 | 2019-04-29 | 15 | 2 | Lauren | 100%
| User manual | 2019-04-27 | 2019-04-29 | 15 | 2 | Lauren | 100%
| Deployment plan | 2019-04-27 | 2019-04-29 | 15 | 2 | Earving | 100%
| Maintence plan | 2019-04-27 | 2019-04-29 | 15 | 2 | Travis | 100%
SET 7: Wind-down
| Testing & Bug-list (req.) | 2019-04-29 | 2019-04-30 | 17 | 1 | Eric | 100%
| Final Github check (all files present) | 2019-04-29 | 2019-04-30 | 17 | 1 | All | 100%
| Clean code (comments, old code) | 2019-04-29 | 2019-04-30 | 17 | 1 | All | 100%
| Presentation script/powerpoint | 2019-04-29 | 2019-04-30 | 17 | 1 | Lauren | 100%